## Slide 1
Domain II Value Driven Delivery
20 % of PMI-ACP Exam
24 Questions

## Slide 2: Agenda
Value Driven Delivery
Assessing values in Agile Projects
Prioritizing Values in Agile Projects
Incremental Delivery
Contracting in Agile Projects
Value, Verification & Validation

## Slide 3: Value Driven Delivery
Maximizing business value through prior authorization incremental delivery testing and validation

## Slide 4: Value Driven Delivery Tasks
Plan work incrementally
Gain consensus on just in time acceptance criteria
Tune process to organization team and project
Release minimal viable product
Work in small batches
Review often
Prioritize work

## Slide 5: Value Driven Delivery Tasks
Refactor code often
Optimize environmental operational it infrastructure factors
Review and checkpoint often
Balance value and risk
Reprioritize to maximize value
Prioritize nonfunctional requirements
Review and improve the overall process and product

## Slide 6: What is Value Driven Delivery?
Projects exist to create business value
The project manager’s goal is to increase value and reduce risk as early as possible
Value-driven delivery has the most weight of the business existence

## Slide 7: Deliver Value Early in the Project
Based on prior translation value is delivered first
The longer a project lasts the more opportunity for risk
By delivering high-value items early, the team demonstrates an understanding of the customers needs
Early value help stakeholders maintain synergy an interest in the project

## Slide 8: Minimize waste is a constant goal
Waste reduces value
Poppendieck’s Seven Areas of Waste:
  Partially done work
  Extra processes
  Extra features
  Task switching
  Waiting
  Motion
  Defects

## Slide 9: Assessing Values in Agile Projects
Value is Expressed in Financial Terms

## Slide 10: Return of Investment (ROI)
Return on investment is the profitability in a project
Return on investment is the value of the project minus the investment in the project
A higher return on investment means you are getting a better return then a lower return –bigger is better
Return on investment is not the best approach to discovering business value in a project

## Slide 11: Present Value
The calculation of a future amount in today’s terms given and assumed interest rate and inflation rate

## Slide 12: Net Present Value
The present value of a revenue stream over a series of time periods
Higher net present values are good

## Slide 13: Internal Rate of Return
Calculates the NPV of the cost of the project and when the NPV of the project meets or exceeds the NPV of the benefits of the project
The higher the IRR the more valuable the project is

## Slide 14: Earned Value Management for Agile Projects
It’s unlikely you’ll see earned value management on the exam
EVM is a suite of formulas to show performance
Earned value compared to actual performance to planned performance

## Slide 15: EVM Foundation
Consider a scenario
BAC = $100,000 for the entire project
As of now EV = $25,000 , AC=$27,000 PV=$50,000

## Slide 16: EVM Foundation
Finding the variance
Cost Variance = EV-AC = 25,000-27,000 = -2,000
Planned Variance= EV-PV = 25,000-50,000 = -25,000
Measuring the performance
Cost Per Index = 25,000/27,000 = .93
Schedule Per Index = 25,000/50,000 = .50

## Slide 17: Predicting the Future
Estimate at completion EAC = BAC / CPI EAC=$100,000/.93 =$107,526
Estimate to Complete ETC= EAC – AC = ETC=$107,526-$27,000 =$80,526

## Slide 18: EAC in Action

## Slide 19: To Complete Performance Index
Efficiency needed to meet BAC: TCPI=(BAC-EV)/(BAC-AC)
TCPI=($100,000-$25,000)/($100,000-$27,000) = 75,000/73,000 =1.0273
Efficiency needed to meet EAC:TCPI=(BAC-EV)/(EAC-AC)
TCPI=($100,000-$25,000)/($107,526-$27,000) =75,000/80,526 =.93
Note:-
Great than 1, hard to accomplish \
Exactly 1, same level of efficiency \
Less than 1, easier to accomplish

## Slide 20: Story Points and EVM
Can use Story Points instead of dollars
Planned to complete 20 story points
Completed 18 instead
SPI=EV/PV =18/20 =.90

## Slide 21: 5 EVM Rules
EV is first
Variance means subtract
Index means division
Less than one is bad in an index
Negative is bad in a variance

## Slide 22: What is Agile Project Accounting?
Agile accounting defines the economic models of agile projects
Project work and smaller chunks of a larger project
Smaller chunks of work are less risky
Agile project accounting is accountability of what was invested in relation to the value of the return on investment

## Slide 23: Key Performance Indicators
Key performance indicators are metrics to show how well the project is performing
  Rate of progress
  Remaining work
  Likely completion date
  Likely cost remaining

## Slide 24: Managing Risk in an Agile Projects
Risk in an agile project is anything that threatens the project’s goals
Risk is considered an anti value
Risk must be managed in a project
Risk identification is an iterative activity
Risk a recorded in a risk along

## Slide 25: Addressing features with high risk
Features that have high levels of risk can be addressed early in project iteration
High areas of risk need to be addressed sooner rather than later
A risk-adjusted backlog brings risk features into an early portion of the project
A risk burndown chart tracks risk as they move down in priority and elimination

## Slide 26: Regulatory compliance for Agile Projects
Regulations are requirements
Regulatory compliance is one instance for documentation where just because is utilized

## Slide 27: Prioritizing Values in Agile Projects
Welcoming Changing requirements is the key to Agile Projects

## Slide 28: Customer Value Prioritization
Agile teams work on the items that yield the highest value to the customer first
The product owner is responsible for keeping items in the backlog prioritized by business value
When changes added to backlog, they must be prioritized for value
The customer is the person who will declare what success looks like
The team will discuss with the customer at the end of each iteration the priority of the remaining work items

## Slide 29: Prioritization Schemes
How the work is prioritized
The team agrees on the prioritization scheme
The prioritization scheme is communicated and agreed upon by the entire agile team

## Slide 30: Simple Scheme for Prioritization
Items in the product backlog are ranked:
  Priority one (high)
  Priority two (medium)
  Priority three (low)
This approach has a risk that everything is ranked as priority one

## Slide 31: MoSCoW Prioritization Scheme
Made popular by DSDM
  Must have
  Should have
  Could have
  Would like to have, but not at this time

## Slide 32: Monopoly Money
Stakeholders receive monopoly money equal to the amount of the project budget
The monopoly money is distributed among the system features
This approach is most effective when it’s limited to prioritizing business features

## Slide 33: 100 Point Method
Each stakeholder is allotted 100 points
The points are assigned to the most important requirements

## Slide 34: Dot Voting or Multi Voting
Stakeholders gets a predetermined amount of dots
Dots are assigned to the business features
Dots could be check marks or stickers

## Slide 35: Kano Analysis
Delighters exciters
Satisfiers
Dissatisfiers
Indifferent

## Slide 36: Requirements @ Prioritization Level
Uses a scale of 1 to 9
Benefit penalty cost and risk of every feature is rated

## Slide 37: Relative Prioritization Ranking
Priority of features
Simplest the features from most important to least important
Determination made to meet budget and schedule
Changes may change the prioritize list
Changes may bump some priorities from the list

## Slide 38: Incremental Delivery
Optimizing the value of delivery

## Slide 39: Incremental Delivery
The team regularly deploys working increments
Usually to a test environment for evaluation
This is an opportunity for an early return on investment

## Slide 40: Minimum Viable Product
Complete enough to be useful
•Small enough that it does not represent the entire project
•Also known as the minimal marketable feature
•Barebones essentials of a product

## Slide 41: Agile Tooling
Agile teams prefer low-tech high-touch tools over-sophisticated computerized models
Technical tools can exclude team members from interacting
Consider high-tech tools for scheduling:
  Data accuracy perception increases
  A bad estimate is a bad estimate
  Barriers for stakeholder interaction are created

## Slide 42: Examples of Low-tech High-touch Tools
Cards
Charts
Information radiator
Tools that promote communication and collaboration
Tools that promote learning and knowledge transfer

## Slide 44: Scheduling Software Vs Kanban Board
Also known as a task board
Help teams monitor the work in progress

## Slide 45: Work In Progress
Also known as a work in process and work in play
WIP is risk
WIP hides bottlenecks
WIP requires investment but delivers no return until the work is complete
WIP needs to be limited

## Slide 46: Limiting Work In Progress
Agile attempts to limit WIP
Kanban boards can have WIP limits
WIP limits keeps the team from taking on too many pieces of work
WIP limits reveal bottlenecks

## Slide 47: Cumulative Flow Diagram
Cumulative flow diagrams help tracking and forecasting the delivery of value
Reveals the total in progress and completed work

## Slide 48: Bottlenecks & Theory of constraints
A constraint is anything that limits your options
Time, cost, and scope are typical constraints
Constraints can be throughput of capacity
A thin line in a cumulative flow diagram can reveal a bottleneck

## Slide 49: Goldratt’s Theory Of Constraints
Five Focusing Steps Of Goldratt’s Theory Of Constraints
Identify the constraint
Exploit the constraint
Subordinate all other processes to exploit the constraint
If after steps two and three is done more capacity is needed to meet demand elevate the constraint
If the constraint has not moved go back to step 1

## Slide 50: Contracting Agile Projects
Exploring Agile Project Contracts

## Slide 51: Request for Proposal
A request for proposal is from the buyer to the seller
If the seller is to use a agile practices it must be defined in the request for proposal
The buyer may need to educate the vendor about agile practices
Agile project welcome change so this may be hard to do with contracts

## Slide 52: Agile Constraints and Contracts
Agile is flexible
Contracts are not flexible
Contracts are a form of a constraint
Contracts are constrained by an offer and a consideration
Collaboration over contracts
Agile projects constrain time and cost
Agile project allow the scope to change
Contracts typically constrain and balance time cost and scope

## Slide 53: Consideration for Contracts
Scope changes
Priorities
Time and cost

## Slide 54: Fixed Price Contract
Both parties share some of the risk and reward
If a vendor delivers on-time they get paid for their work at the hourly rate
If the vendor delivers early they get paid for their work but at a higher hourly rate
If the vendor delivers late they get paid for their work but at a lower

## Slide 55: Fixed Price Work Packages
The price of the work remains constant
Individual work packages are estimated for cost
Changes to the scope reflect a new estimate for those work packages

## Slide 56: Customize Contracts
The buyer and the seller can make any agreement they want
Procurement is always tricky with agile projects

## Slide 57: Value, Verification & Validation
Ensuring Value with Agile Projects

## Slide 58: Gulf of Evaluation
The difference between what is said and what is understood
Intangible projects often experience this gulf
What does done looks like?

## Slide 59: Frequent Verification and Validation
Testing checkpoints and reviews
Frequent verification and validation happened throughout the project
Build consensus between the project team and the project stakeholders

## Slide 60: Examples of Verification and Validation in XP
Pair programming
Unit testing
Customer collaboration
Stand up meetings
Acceptance testing
Iteration demonstrations
Product release

## Slide 61: Exploratory Testing
The tester aims to discover issues and unexpected behavior
The tester explores the software
This is in addition to scripted testing

## Slide 62: Usability Testing
How will a user respond to the system under realistic conditions?
How easy is it to use the system?
What improvements need to be made for usability?

## Slide 63: Continuous Integration in Agile Projects
Incorporate new and changed code into the code repository
Small code commits
Frequent integration
Relies on automated tools to integrate code when new code is checked in

## Slide 64: Continuous Integration System
Source code control system –version control
Build tools –build tools compile the code
Test tools –unit test to ensure functionality operates as expected
Scheduler or trigger –builds are launched on a schedule or based on conditions
Notifications –an email or instant message reporting on the results of a build

## Slide 65: Why Continuous Integration?
Early warning a broken conflicting or incompatible code
Problems are fixed as they occur
Immediate feedback
Frequent unit testing define issues quickly
Easy to reverse the code back to the last known good

## Slide 66: Disadvantages of Continuous Integration
Set up time is lengthy
  Often called Iteration 0
Cost of a dedicated server
Time required to build a suite of automatic tests

## Slide 67: Exploring Test Driven Development
Also called test first development
•Test are written before the code is written
  Nunit
  Junit
•Code is developed and edited until the code passes all tests
•Refactoring is the final step to clean up the code

## Slide 68: Test Driven Development
Red –green –re-factor
Red –green –clean
Focus on the test first
Early testing helps catch defects early in development
Beware of developers writing their own test

## Slide 69: Acceptance Test Driven Development
Testing focus is on business requirements
Test represent the functionality the software is to have
It’s all about the desired behavior
FIT –framework for integrated testing
  Also called FitNessee
  http://www.fitnesse.org/

## Slide 70: Acceptance Test Driven Development Cycle
Discuss the requirements –developers as the product owner questions that are designed to gather acceptance criteria
Distill test in a framework friendly format –gets the test ready to be entered into the acceptance test tool
Developed the code and run the test –test initially fail because the code hasn’t been written completely
Demo –with automated acceptance testing scrips and demonstrations of the software

## Slide 71: Domain Completion
You have successfully completed –
Value Domain Delivery domain
PMI-ACP