## Slide 1
Domain V Adaptive Planning
12% of PMI-ACP Exam
14 Questions

## Slide 2: Adaptive Planning
Planning an Agile Project

## Slide 3: Agenda
Adaptive Planning Overview
Agile Planning Concepts
Tools for Agile Project Sizing and Estimating
Planning for releases and iterations

## Slide 4: Adaptive Planning Overview
Overview

## Slide 5: Key Tasks for Adaptive Planning
Progressive elaboration and rolling wave planning
Transparent planning and key stakeholders
Managing expectations by refining plans
Adjusting planning cadence based on project factors and results
Inspect and adapt the plans to changing events
Size items first independently of team velocity
Adjust capacity for maintenance and operations demands to update estimates
Start planning with high-level scope schedule and cost range estimates
Refine ranges as the project progresses
Use actuals to refine the estimate to complete

## Slide 6: What is Adaptive Planning?
Planning is an ongoing activity
Agile planning is different than predictive planning
Plan for early delivery business value, risk reduction, visibility

## Slide 7: Interactive Planning Examples
Daily standup
Backlog prioritization
Sprint retrospective
Iteration planning

## Slide 8: Agile Planning Concepts
Planning an Agile Project

## Slide 9: Beginning Adaptive Planning
Agile projects are value-driven
Minimize non-value-added work
Plan to replan
Early plans are necessary, but they’re likely flawed
Uncertainty requires replanning

## Slide 10: Agile Versus Non-Agile Planning
Trial and demonstration uncover true requirements
Less up front and more iterative planning
Mid-course adjustments are normal

## Slide 11: Trial and Demonstration
Prototypes help initial planning
Helps to avoid the gulf of evaluation
Communicate agile planning practices

## Slide 12: Iterative Planning
The planning effort is distributed throughout the project life cycle
Agile projects are risky
Consider planning efforts over the project life cycle
Agile projects typically do more planning

## Slide 13: Planning Risk Graph

## Slide 14: Changes to Plan are Normal
Knowledge work doesn’t follow a predictive plan

## Slide 15: Principles of Agile Planning
Plan at multiple levels
Engage the team and customer in planning
Demonstrate progress in velocity
Taylor processes for the project
Priorities will cause the plan to be updated
Account for risk distraction and team availability
Utilize estimate ranges
Base projections on completion rate
Factor in diversion from outside work

## Slide 16: Agile Discovery
Emergent plans and designs versus predictive plans and designs
Pre planning activities together consensus
Backlog refinement –grooming
Estimating uncertain work forces certain work
New product development vs. Repeatable project

## Slide 17: Progressive Elaboration
As more information becomes available more planning can happen
Continuing steadily in small increments
Progressive elaboration examples
  Plans
  Estimates
  Risk assessments
  Requirements definition
  Software design
  Test scenarios

## Slide 18: Progressive Elaboration and Rolling Wave Planning
Rolling wave planning is planning a multiple points
Plan and execute iteration
Progressive elaboration is incorporating new information into the plans
Progressive elaboration is the implementation of rolling wave planning

## Slide 19: Value based analysis
Assessing and prioritizing the business value of work items
Business benefit –cost
  Business benefit equals $8,000
  Cost equals $5,500
  Value is $2,500

## Slide 20: More Value based analysis
Will the item generator business value every week or month
A high business value item may be dependent on a low business value item

## Slide 21: Value based decomposition
Requirements elicitation
Grouping of like features
Breaking down of features
Ranking of requirements
Prioritize requirements into development

## Slide 22: Creating a Product Box
Imagine a product box or software
Top three features
Major functional elements
Prioritization of features
This is a visualization exercise

## Slide 23: Coarse Grained Requirements
Keeps the overall design balanced
Delays decision on implementation details until the last responsible moment

## Slide 24: Time boxing in an Agile Projects
Fix duration period of time
Define set of activities
Daily scrum or stand up
  Daily standup meetings -15 minutes
  Retrospective –2 hours
  Iterations and sprint’s –1 to 4 weeks

## Slide 25: Timeboxing Sprints
12 work items
Team completes eight
Remaining four items returned to the backlog

## Slide 26: Parkinson’s law
Work expands to fill the time allotted to it
Student syndrome –students wait to the last possible minute to start working

## Slide 27: Tools for Project Sizing & Estimating
Estimating an Agile Project

## Slide 28: Providing Estimate Ranges
Not as precise as predictive planning
More uncertainty and agile projects
Include a range of variance
  Between $500,000 and $550,000
  Plus or minus 10%

## Slide 29: Estimate Convergence Graph

## Slide 30: Creating an Agile Estimates
Why is an estimate needed –to create a schedule and budget
When does estimating happen –the last responsible moment and throughout the project
Who does the estimating –team members estimate their own work
How are estimates created –stages of sizing and planning; roll out an estimate cost may also be included
How are estimates stated –always include a degree of uncertainty

## Slide 31: Factoring an Ideal time
Estimate as if there would be no interruptions
Ideal time assumes all time in the estimate is for project work

## Slide 32: Assumptions for sizing & estimating
Details emerged as the project moves forward
Plans are adjusted based on feedback
Privatization happens throughout the project

## Slide 33: Decomposition of Project Requirements
Breakdown of the project work
Epics –large user stories that span one or more iterations
Feature –attributes of the product
User story –decomposition of a feature
Task –smallest element of the decomposition

## Slide 34: What is a user story?
Small chunk of business functionality within a feature that involves roughly 1-3 days work
Also defined as for 40 hours of work
User stories are written on index cards or sticky notes
User stories are the items in the product backlog

## Slide 35: Creating a user story
Potential stories are called candidate stories
Perspective of the user or customer
Often written in the following format
As a role I want functionality so that business benefit
Answers two questions:
  Who was asking for this?
  Why are we doing this?

## Slide 36: User Story Format
Given –the scenario for the story
When –the action that takes place
Then –the result of the action

## Slide 37: 3 C’s of User Story
Card –just enough text to identify the story
Conversation –details are communicated via a conversation between the customer and the development team
Confirmation - customer confirmed the story has been implemented correctly

## Slide 38: INVEST in User Stories
Characteristics of effective user stories follow INVEST:
Independent –stories can be prioritized in any order
Negotiable –the team can discuss the user story with the product owner and make trade-offs based on the cost and function
Valuable –the user story must have obvious value
Estimate –the user story can be estimated for effort
Small –small user stories are easier to create and test that large user stories; 4 to 40 hours work
Testable –the story results must be testable

## Slide 39: Defining the User Story backlog
Also known as the product backlog
User stories are listed and sorted
User stories are prioritized in the backlog
There is only one backlog

## Slide 40: Grooming the backlog
The backlog needs to be kept continuously updated
Prioritizing or refining the backlog is called grooming

## Slide 41: Changes to the backlog
New stories can be added
Existing stories maybe reprioritized or removed
Stories can be decomposed into smaller chunks
Customer or value management team can add new story or reprioritize existing stories
Decomposing stories –also called slicing –is typically done by the development team

## Slide 42: Relative Sizing of Story Points
It’s difficult to make absolute estimate
Story points are points assigned to stories size
Relative sizing assigns points to stories on a relative scale
The team then decides how many points can be done in our generation

## Slide 43: The Fibonacci Sequence
Starting with zero the two numbers in the sequence are added together to get the next number
0 plus 1 equals one
One plus one equals two
2 plus 1 equals 3
1, 2,3,5,8,13,or 21 points
Only these numbers are assigned
to user stories

## Slide 44: Fibonacci Sequence

## Slide 45: Guidelines for story points
The team owns the definition of their story points
Story point estimate should be all inclusive
Point sizes should be relative
When disaggregating estimates the totals don’t need to match
Complexity work effort and risk are all included in the estimate

## Slide 46: Affinity Estimating
Grouping items into similar categories or collections
Group items based on story points
Affinity estimating is like triangulation
Allows the team to see the collection of user stories by points assigned

## Slide 47: T-Shirt Sizing
User stories are assigned to t-shirt sizes

## Slide 48: Story Maps
High-level planning tool to map out project priorities
Prioritized matrix of the features and user stories for the product being built
Backbone –top level of the story map; essential functions for the system to work
Walking skeleton –second row of the story map; smallest version of the system that will beat the customers both basic needs

## Slide 49: Creating Product Roadmap
Visual depiction of product releases
Primary items that will be included in each release
Helps to check risk and viability

## Slide 50: Wideband and Delphi
Rounds of anonymous estimates
Helps to build consensus
  Bandwagon effect –gathering around common viewpoint
  Highest-paid person’s opinion –HIPPO
  Groupthink –making decisions to maintain group harmony

## Slide 51: Planning Poker
Cards with the Fibonacci sequence
User stories review
Participants show their cards at the same time the score the user

## Slide 52: Planning for Releases& Iteration
Agile Projects are divided into releases & iterations

## Slide 53: Defining Releases & Iterations
Iterations are short, timeboxed periods of development
Usually last two to four weeks
Releases are the publishing of the software

## Slide 54: Defining Iteration Types
Development timeboxes
Sprints
Time for development

## Slide 55: Iteration Zero
Sets the stage for development
Typically no deliverables for the customer
Prepares to do the work

## Slide 56: Iteration H
Hardening sprint
Wrap up sprint
Used to stabilize the code
Document the product
Compile final assembly
Final testing

## Slide 57: Architectural Spikes
Proof of concept
Timeboxed effort to test the approach

## Slide 58: Risk Based Spike
Short effort to investigate risk
Reduce or eliminate through mitigation
Good for new technology and early in the project

## Slide 59: Fast Failure
Testing of different approaches for viability
Good result before wasting time and money

## Slide 60: High level planning - Visioning
Prior to planning the first release
Mapping out the overall effort of the project
Product owner and sponsor
Key team members
Other major stakeholders

## Slide 61: Outputs of High Level Planning
Updated prioritize backlog
Coarse grained relative estimates for each user story
Goals of the release
Release date

## Slide 62: Hosting a Release Planning Meeting
All stakeholders represented
Happens before each release
The goal is to find which stories will be done in which iterations for the release
Also defines future iterations for future releases
Assess the prioritize backlog
Reviews story sizing
Sort the stories by release
Define the initial outline or road map for the release
Slice the stories as needed for the plan release

## Slide 63: More about slicing stories
Compound stories –includes other independent stories within
Stories –one large complicated story; usually can’t fit in one iteration

## Slide 64: Iteration Planning
Meeting for and facilitated by the delivery team
Confirms goal for the current iteration
Discuss the user stories in the backlog
Select the user stories for the iteration
Define the acceptance criteria and write the acceptance test for the stories
Breakdown the use for stories in tasks
Estimate the task

## Slide 65: Velocity for Finding an estimates
Base of the teams velocity more accurate estimates can be created
Burn up charts
Burndown chart

## Slide 66: Hosting the Daily Standup
Also known as the daily scrum
Call the stand up because the team’s stand through the meeting
15-minutes duration
Answer three questions
  What have you worked on since our last meeting?
  What will you finish today?
  Are there any problems or impediments to your progress?

## Slide 67: Rules for the Daily Standup
People with tasks must attend
Only people who have tasks can talk
Address the entire team not the scrum master
No side conversations
Add new task to sticky notes if they are started
Discuss issues after the stand up
Solve problems offline

## Slide 68: Domain Completion
You have successfully completed –
Adaptive Planning domain
PMI-ACP