## Slide 1
Domain VI
Problem Detecting & Resolution
10 % of PMI-ACP Exam
12 Questions

## Slide 2: Agenda
Problem Detection & Resolution Overview
What is the Problem?
Detecting Problem in Agile Projects
Managing Threats & Issues

## Slide 3: Problem Detection & Resolution Overview
Overview

## Slide 4: Problem Detection and Resolution Tasks
Create a safe an open environment to surface problems
Engage team in resolving threats and issues
Resolve issues or reset expectations
Maintain a visible list of threats and issues
Maintain a threat list and add threat remediation efforts to the backlog

## Slide 5: 4 Themes in Resolution Tasks
Understanding problems
Detecting problems
Managing threats and issues
Solving problems

## Slide 6: Risk Management
Risk are uncertain events or conditions
An agile projects risk are always negative
Probability and impact
Risk identification and tracking

## Slide 7: What is the Problem?
Problem & Agile Projects

## Slide 8: Issues and Risks
Risk are uncertain events they’ve not yet happened
Issues are risk events that have occurred

## Slide 9: Truly understand the problems of resolution
Problems can mushroom
Problems can have ripple effects
What happens in one area of the project affect all other areas of the project

## Slide 10: Financial Impact of Problems
The longer a defect is left unaddressed, the more expensive it will be to fix
It is like going to the dentist
The longer you wait the more expensive it will be

## Slide 11: Where issues are discovered?

## Slide 12: Reviewing Technical Debt
Backlog of work caused by lack of regular clean-up maintenance and standardization
Refactoring solves technical debt
Red green refactor
Refactoring cleans up and standardize is code to make it easier to support
Refactoring should be included in estimates

## Slide 13: Creating a Safe Environment
PMI-ACP calls for safe and open environment
People should feel comfortable experimenting for solutions
When people get stuck they should share the problem with her teammates
Safe environments are coaching opportunities

## Slide 14: Understanding Failure Modes
We make mistakes –mistakes happen
We prefer to fail conservatively
We prefer to invent rather than research
We are creatures of habit
We are inconsistent

## Slide 15: Understanding Success Modes
We are good at looking around
We are able to learn
We are malleable
We take pride in our work

## Slide 16: Creating success strategies
Balance discipline with tolerance
Start with something concrete and tangible
Copy and alter
Watch and listen
Support both concentration and communication
Match work assignments with a person
Retain the best talent
Use rewards that preserve joy
Combine rewards
Get feedback

## Slide 17: Detecting Problems in Agile Projects
Finding Problem & Defects

## Slide 18: Start with Daily Startup
Are there any problems or impediments to the team members?
This is the first step to detecting problems

## Slide 19: Reviewing Lead Time & Cycle Time
Lead time is how long something takes to go through the entire process
For example from concept design to shipping
Cycle time is a subset of lead time
Cycle time is how long something takes to go through a part of the process
For example from coding to testing

## Slide 20: Lead Time & Cycle Time on a Kanban Board

## Slide 21: Cycle Time, WIP & Throughput
Understanding the team’s throughput allows for forecasting future capabilities
Cycle time equals WIP / throughput

## Slide 22: Project Cycle Time
The project duration is the cycle time for the entire project
Average amount of work the team can get done in a time.
Productivity is the rate of efficiency at which the work is done
Productivity could be the amount of work done per team member

## Slide 23: Looking for Defect Cycle Time
Defect cycle time is the amount of time between when the defect was discovered and when the defect was fixed
The longer the defect cycle time typically the more expensive the defect

## Slide 24: Defect Rates
Defects that slip by the testing team are called escaped defects
Escape defects are the most expensive to fix
The defect rate measures the frequency of defects found
An increase in escape defects signals a problem with a process

## Slide 25: Variance Analysis
The difference between what was planned and what was experienced
Cost variance
Schedule variance
Other tracking items

## Slide 26: Causes of Variance
Average day to day differences
  Good days and bad days
  Ups and downs
Special causes of variance
  Something unusual that causes a problem
  Power went out for 2 days
  Three team members caught the flu

## Slide 27: Relying on Trend Analysis
Measurements of past experiences are called lagging metrics
Leading metrics provide a view into the future
Trend analysis aims to predict performance or problems

## Slide 28: Control Limits
Upper and lower control limits
Set boundaries and expectations for performance
WIP and Kanban are a form of control limits

## Slide 29: Managing Threats & Issues
Removing Anti Value in Agile Projects

## Slide 30: Working with Risk adjusted backlog
Risk is considered anti value
Goal is to attack high-risk items early in the project
Items with the greatest value in greatest risk move to the top of the backlog

## Slide 31: Backlog Grooming for Risk
Stories are ranked based on business value and risk level
The ranking is subjective often based on gut feeling or preference
The return on investment for the project can be broken down per item
The business representatives assign the ROI to each item in the backlog

## Slide 32: Finding the expected monetary value
Expected monetary value is the worth of a risk event
EMV =risk impact x risk probability
EMV = $45,000 x 30%
EMV = $13,500
This is done for each risk in a probability impact matrix

## Slide 33: Probability Impact Matrix

## Slide 34: Risk Severity
Instead of risk probability and dollar amounts
Probability and impact uses a simple scale
For example low medium high
Risk severity =risk probability x risk impact
Risk severity = 3 x 1

## Slide 35: Risk Burn Down Chart
Stacked area graphs of cumulative project risk severity
Visual communication of risk events
Severe these for each risk are plotted on top of one another to show the cumulative severity of the project
Overtime risk should diminish so the chart diminishes as well

## Slide 36: Solving Problems
Solving Problems for Agile Projects

## Slide 37: Problem Solving is Continuous improvement
Problem solving games to fix the problem before it happens
Consider daily standup
Iteration reviews and retrospectives
Sprint planning sessions

## Slide 38: Engage the team in problem solving
By asking the team for a solution we inherit consensus for the proposal
Engaging the team excesses a broader knowledge base
Team solutions are practical
When consulted people work hard to generate good ideas
Asking for help shows confidence
Seeking others ideas models desired behavior

## Slide 39: Considerations for Team Engagement
Involve the team where it can be most helpful
Solve real problems only
Team cohesion is necessary
Check in after project changes
Be sure to follow through

## Slide 40: Some problems can’t be solved
Even with team engagement some problems won’t find a solution
Work around these problems
Track and monitor the problems

## Slide 41: Domain Completion
You have successfully completed –
Problem Detecting & Resolution domain
PMI-ACP